## PERT-CPM
CENFOR - PROJECT SCHEDULE
| ê | ì | ê | ì | ê | ì | ê | ì
1. Conception of Idea: August 2007
3. Clearance and Approval of UPV Authorities: October 2007
5. Collection of Seeds, Potting and Maintenance of Nursery: December 2007 - Present
7. Planting of the Seedlings: June 1-30 2008
2. Planning Stage: September 2007
4. Communication of the Program to Brods and other Parties: November 2007 - Present
6. Preparation of the Site for Planting: May 2008
8. Launching of the CENFOR and Maintenance: July 14, 2008
9. Maintenance , Nurturing and Monitoring: July 14, 2008 and onwards

## GANTT CHART
CENFOR - PROJECT PROGRESS EVALUATION | [6 empty] | Completed
On going
For Implementation
NO. | TASKS | START | END | DURATION |  | Q3 2007 |  |  | Q4 2007 |  |  | Q1 2008 |  |  | Q2 2008 |  |  | Q3 2008 |  |  | Q4 2008 |  |  | 2009 |  |  |  | 2010
[6 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Jul
1 | CONCEPTION OF IDEA
| Discussion and agreementamong members | 2007-08-27 | 2007-08-27 | 1 | days
2 | PLANNING STAGE
| Involvement of Brods | 2007-09-15 | 2007-10-15 | 30 | days
| Technical Consultations | 2008-10-15 | 2007-12-21 | 65 | days
| Design of the Cenfor | 2008-10-15 | 2007-12-21 | 65 | days
3 | CLEARANCE AND APPROVAL
OF UPV AUTHORITIES
| Request letter for the Chancellor | 2007-12-15 | 2008-01-15 | 30 | days
| Drafting of MOA | 2008-01-12 | 2008-02-14 | 30 | days
| Signing of MOA | 2008-05-01 | 2008-05-07 | 7 | days
4 | COMMUNICATION OF CENFOR
TO OTHER ALUMNI CHAPTERS AND
OTHER PARTIES
| Design and creation of brochure | 2008-11-15 | 2008-12-21 | 36 | days
| Design and creation of website | 2008-12-21 | 2008-01-15 | 21 | days
| Dessimination of the program | 2008-01-01 | Current
5 | COLLECTION OF SEEDS, POTTING
AND MAINTENANCE OF NURSERY
| Collection of seedlings | 2007-12-05 | Current
| Potting of seeds | 2008-01-07 | Current
| Watering | 2008-01-07 | Current
| Initial Fertilization | 2008-01-07 | Current
6 | PREPARATION OF THE SITE
| Clearing of Site | 2008-05-10 | 2008-05-11 | 2 | days
| Set up of Fence | 2008-05-17 | 2008-05-18 | 2 | days
| Wall of Donors | 2008-05-23 | 2008-05-24 | 2 | days
| Name plates | 2008-05-23 | 2008-05-25 | 2 | days
| Construction of Fence | 2008-05-31 | 2008-06-01 | 2 | days
7 | PLANTING OF THE SEEDLINGS
| 1st Planting Schedule | 2008-06-07 | 2008-06-07 | 1 | days
| 2nd Planting Schedule | 2008-06-14 | 2008-06-14 | 1 | days
| 3rd Planting Schedule | 2008-06-21 | 2008-06-21 | 1 | days
| 4th Planting Schedule | 2008-06-28 | 2008-06-28 | 1 | days
8 | LAUNCHING OF THE CENFOR
AND MAINTENANCE
| Invitations to Brods and other Chapters | 2008-07-01 | 2008-07-06 | 7 | days
| Preparation for Launching Day | 2008-07-07 | 2008-07-12 | 5 | days
| CENFOR - Launching | 2008-07-14 | 2008-07-14 | 1 | days
| Maintenance for Next Three Years | 2008-07-14 | onwards | 1095 | days

## PROJECT COST ESTIMATION
CENFOR - PROJECT SCHEDULE
ACTIVITY |  | LEAD PERSONS | TIMETABLE | STATUS |  | RESOURCES NEEDED
[5 empty] | Item | Quantity | Unit | Cost/Unit | Total
1 | CONCEPTION OF IDEA | Brod Ulysses Alama | 2007-08-27 | Done
Brod Froilan Nazareno
Brod Jun Banagodos
Brod Alvin Natividad
Brod Taui Jamile
Brod Greg Panigbatan
2 | PLANNING STAGE | Brod Ulysses Alama | 2007-09-01 | Done
Brod Froilan Nazareno
Brod Greg Panigbatan
Brod Shan Buyco
Brod Randy Malayao
Brod November Romena
Brod Jay Pascual
3 | CLEARANCE AND APPROVAL | Brod Ulysses Alama | 2007-10-01 | Done
| OF UPV AUTHORITIES | Brod Froilan Nazareno
Brod Taui Jamile
Brod Otep Arbiol
Brod Sammy Malvas
4 | COMMUNICATION OF CENFOR
TO OTHER ALUMNI CHAPTERS AND
OTHER PARTIES
| Design and Creation of the Brochure | Brod Jay Pascual | 2007-11-15 | Done | Brochures | 1000 | pcs | 8 | 8000
| Design and Creation of the Website | Brod Jay Pascual | 2007-11-15 | Done | Website | 1 | pcs | 15000 | 15000
| Desimmination of the Program | Members of UPVBSFAA | 2007-11-15 | On Going
5 | COLLECTION OF SEEDS, POTTING
AND MAINTENANCE OF NURSERY
| Collection of Seeds/Seedlings | Brod Jun Banagodos | 2007-12-05 | On Going | Plastic Trays | 5 | pcs | 500 | 2500
Members of UPVBSFAA
| Potting of Seeds/Pest Control | Brod Ulysses Alama | 2008-01-07 | On Going | Polybags | 5000 | pcs | 0.5 | 2500
Members of UPVBSFAA
| Watering | Brod Ulysses Alama | 2008-01-07 | On Going | Water Hose | 50 | meters | 10 | 500
Members of UPVBSFAA
| Initial Fertilization | Brod Ulysses Alama | 2008-01-07 | On Going | Fertilizer | 1 | sack | 1250 | 1250
6 | PREPARATION OF THE SITE
| Clearing of Areas | Brod Ulysses Alama | May 10-11, 2008 | For Implementation | Jungle bolo | 10 | pcs | 250 | 2500
| Digging of Holes | Brod Ulysses Alama | May 17-18, 2008 | For Implementation | Shovel | 10 | pcs | 400 | 4000
[5 empty] | Iron Bar/"Bareta" | 10 | pcs | 350 | 3500
[5 empty] | Labor of digging | 2500 | holes | 5 | 12500
| Set up of fence | Brod Ulysses Alama | May 30-31, 2008 | For Implementation | Long Bamboo | 240 | pcs | 25 | 6000
[5 empty] | Hard Bamboo Pole | 200 | pcs | 6 | 1200
[5 empty] | Labor for fencing | 12 | persons | 500 | 6000
[5 empty] | Nails | 15 | kilos | 75 | 1125
[5 empty] | Galvanized wire | 25 | kilos | 60 | 1500
| Wall of Donors | Brod Ulysses Alama | 2008-06-01 | For implementation | Cement | 15 | sacks | 200 | 3000
| ( 1.5 meter x 6 meter concrete wall) |  |  |  | Sand Gravel | 2 | cu. m. | 370 | 740
[5 empty] | Gravel | 2 | cu. m. | 470 | 940
[5 empty] | "Kabilya" | 20 | pcs | 118 | 2360
[5 empty] | Bricks | 200 | pcs | 15 | 3000
[5 empty] | Hollow blocks | 200 | pcs | 9.8 | 1960
(4X8X16)
| Name Plates of Donors |  |  |  | Iron Plates | 200 | pcs | 20 | 4000
[5 empty] | Puncher | 1 | pcs | 3500 | 3500
7 | PLANTING OF THE SEEDLINGS
| 1st Planting Schedule | Brod Ulysses Alama | 2008-06-07 | For Implementation | lunch and snack | 25 | pax | 200 | 5000
| > 25 persons at 25 plants per person | Members of UPVBSFAA
| 2nd Planting Schedule and Fertilization | Brod Ulysses Alama | 2008-06-14 | For Implementation | lunch and snack | 25 | pax | 200 | 5000
| > 25 persons at 25 plants per person | Members of UPVBSFAA
| 3rd Planting Schedule and Fertilization | Brod Ulysses Alama | 2008-06-21 | For Implementation | lunch and snack | 25 | pax | 200 | 5000
| > 25 persons at 25 plants per person | Members of UPVBSFAA
| 4th Planting Schedule and Fertilization | Brod Ulysses Alama | 2008-06-28 | For Implementation | lunch and snack | 25 | pax | 200 | 5000
| > 25 persons at 25 plants per person | Members of UPVBSFAA
8 | LAUNCHING OF THE CENFOR
AND MAINTENANCE
| Invitations to other Chapters, Guests, | Brod Greg Panigbatan | July 1-6, 2008 | For Implementation | Invitation Cards | 200 | pcs | 15 | 3000
| Local Media and Student Leaders | Members of UPVBSFAA
| Preparation for the Launching Day | Brod Gil "Ding" Severino | July 7-12, 2008 | For Implementation | Drop Banners | 5 | pcs | 500 | 2500
|  | Members of UPVBSFAA |  |  | Cenfor T Shirts | 200 | pcs | 150 | 30000
| Launching | Brod Alvin Natividad | 2008-07-14 | For Implementation | Food and Drinks | 100 | pax | 175 | 17500
|  | Members of UPVBSFAA |  |  | Audio System Rental | 1 | set | 5000 | 5000
[5 empty] | Chairs and Tables Rental | 200 | pax | 20 | 4000
[5 empty] | Canopy Rental | 5 | set | 2500 | 12500
| Maintenance for the next three years | Brod Ulysses Alama | July 14 - Onwards | For Implementation | Yearly labor for | 3 | pax | 126000 | 378000
|  | Members of UPVBSFAA |  |  | maintenance
(watering,weeding,fertilization)
@ P 3,500/person
per month for next 3
years
[5 empty] | Fetilizers | 12 | sacks | 1250 | 15000
1 sack per/quarter
for 3 years
[5 empty] | Sprayer | 1 | pcs | 7500 | 7500
[5 empty] | Water Pale/Buckets | 10 | pcs | 100 | 1000
[6 empty] | TOTAL |  |  | 583575

## SEEDLINGS INVENTORY
CENFOR - SEEDLINGS INVENTORY
NO. | TYPE OF TREE | POTTED | GERMINATED | STATUS | TARGET SEEDLINGS Waiting for Donations
| HARDWOOD |  |  |  | 1 | Almasiga
1 | Acacia | 100 | 100 |  | 2 | Guiho
2 | Apitong | 18 | 18 |  | 3 | Ilang Ilang
3 | Arbor Tree | 100 | 60 |  | 4 | Kamuning
4 | Benguet Pine | 100 | 0 |  | 5 | Laua-an
5 | Dao | 320 | 0 | Slow germinating type of tree | 6 | Magkono
6 | Kamagong | 300 | 0 |  | 7 | Palosapis
7 | Mahogany | 20 | 18 | Slow germinating type of tree | 8 | Tangile
8 | Molave | 200 | 0 | Recently potted | 9 | Tindalo
9 | Narra | 700 | 450 | Recently potted | 10 | Yakal
10 | Palawan Cherry | 150 | 20 | Low survival rate/lack of technical know how
11 | Payhud | 100 | 70 | Recently potted
12 | Teakwood | 300 | 50
13 | Udling | 180 | 150
| Sub-Total | 2588 | 936
FRUIT BEARING
1 | Batuan | 18 | 0
2 | Cacao | 60 | 30
3 | Chico | 14 | 8
4 | Kaimito | 30 | 24
5 | Kamonsil | 20 | 20
5 | Langka | 200 | 200 | Recently potted
6 | Mabolo | 300 | 0
7 | Makopa | 3 | 0 | Slow germinating or bad seed
8 | Pili | 114 | 15 | Bad seed
9 | Pomelo | 4 | 0 | Slow germinating or bad seed
10 | Santol | 17 | 0 | Recently potted
| Sub-Total | 780 | 297
ORNAMENTAL
1 | Fox Tail Palm | 10 | 10
2 | Ordinary Palm | 120 | 100
3 | Royal Palm | 150 | 50
| Sub-Total | 280 | 160
| GRAND TOTAL | 3648 | 1393